| Contract for works Project “U-LEAD: SALAR Support to the Roll-out phase” 2018-2020 This document was produced with the financial assistance of the European Union and Sweden - The Parties SKL International AB, with company number SE556414420101, represented by Jenny Jansson Pearce, Managing Director, hereinafter referred to as the Investor - the one who coordinates the project: organizes, finances and controls the implementation of the work, in order to achieve the social effect – refurbishment works in the premises of the Administrative service center in the city of Buryn, Sumy region. Bank details: IBAN: SE52 8000 0890 1194 4867 7196 Acc. No: 8901-1 944 867 719-6 BIC/Swift: SWEDSESS Bank: Swedbank AB Bank address: 105 34 Stockholm, Sweden and Buryn City Council of Sumy region represented by by Mayor Ladukha Viktor Borysovych, EDRPOU 04058025, hereinafter reffered to as the Client - the owner/user of the land plot, which performs the role of the building owner, provided by the city-planning legislation of Ukraine, which receives the initial data for the design of the object, approves the construction project, draws up the documents granting the right to perform construction works, hereinafter reffered to as “Works” controls execution of construction works, takes into operation the finished construction object, issues ownership, is responsible for connecting the object to technical networks and concluding maintenance contracts object and is responsible for Works execution as the building owner as stipulated by the Law of Ukraine "On the regulation of urban development." and «XXXXXX» represented by XXXXXX hereinafter referred to as the Contractor - the one who is obliged to execute and to deliver the completed work with the use of his own work materials specified in Section 1.3 of this Contract for Works to the Investor and the Client in accordance with the design estimates, state building regulations and current legislation. Bank details: « XXXXXX » Address: EDRPOU No. Bank address: SWIFT code: IBAN: have concluded this Contract for the execution of Works (hereinafter, the “Contract”) as described in the sections below. The three parties together are hereinafter referred to as the Parties. This Contract is part of the International Technical Assistance U-LEAD with Europe: Ukrainian Local Empowerment, Accountability and Development Programme (U-LEAD), Component 2: Administrative Service Centers, roll-out phase extension dully registered with the Ministry of Economic Development and Trade, registration card number 3722-03. 1.2 Contact details The point of contact for each party shall be authorized to represent the party in all matters regarding the performance according to the agreed commitments in the Contract. SKL International. Street address:; Hornsgatan 15. Postal code:; 118 82. City:; Stockholm. Country:; Sweden. Point of contact regarding the Contract, name:; Alexander Mazurkin. Email address to the point of contact; alexander.mazurkin@skr.se. Telephone number to the point of contact:; +46 76-1251913. Buryn City Council. Street address:; 1 Pershotravneva Str.. Postal code:; 41700. City:; Buryn, Sumy region. Country:; Ukraine. Point of contact regarding the Contract, name:; Ladukha Viktor Borysovych. Email address to the point of contact:; buryn.rada@ukr.net. Telephone number to the point of contact:; +380668607468. «XXXXXX». Street address:. Postal code:. City:. Country:. Point of contact regarding the Contract, name:. Email address to the point of contact:. Telephone number to the point of contact:. 1.3 Subject Matter of the Contract The Contractor undertakes to deliver the interior finishing works (refurbishment), to install a ventilation system, internal power supply networks, water supply and sewerage, fire protection works in the premises of the Administrative service center by the order, engineering documentation, and project design document agreed by the Client and the Investor beforehand, including the supply of the materials, hereinafter referred to as the Works, with the rates stated in Appendix 1 Activity Dependent Cost Estimate and Specification Requirements hereinafter referred to as the Appendix 1 to present Contract, at address of the refurbishment works: city of Buryn, 1 Pershotravneva Str., according to the terms and conditions in the present Contract with appendices. The Works shall be delivered with the skill, speed and care that the Investor and the Client have reason to expect from a reputable company in the industry. The Contractor shall, when delivering the Works, comply with all applicable laws, regulations, norms and regulations issued by state and municipal government agencies and that are applicable to the undertaking of the Contract, as well as provisions of state building codes and standards that determine the requirements for construction work. 1.4 Responsibilities The Contractor undertakes to deliver the Works to the Investor and the Client according to the terms and conditions of this Contract with appendices which are the integral part of this Contract. The responsibilities of the Contractor include the following: - The Contractor is responsible for the protection of the object and the preservation of materials. The cost of the object protection must be included in the total value of the Contract; - The Contractor is responsible for organization of temporary power and water supply for construction needs. Тhe cost must be included in the total value of the Contract. Costs that cannot be forseen due to government action or likewise due to the the introduction of a quarantine on the Territory of Ukraine by Resolution on Prevention of the Spread of COVID-19 in Ukraine dates 11 March 2020 of the Cabinet of Ministers of Ukraine or any other future resolution put in its place will be paid by the Investor if, and only if, the Investor beforehand has given its written consent to pay such costs. Such unforeseeable costs should therefore not be included in the total value of the Contract. - The Contractor is responsible for the organization of construction site temporary fencing, driveways and mounting object’s passport which shall be provided by the Client; - The Contractor is responsible for the timely and high-quality documentation at the construction site; - The Contractor is fully responsible for the organization of labor protection services at the object, conducting briefings, providing workers with personal protective equipment, etc. The Contractor must respond within 24 hours to the comments of the Client or Investor and take measures to eliminate the identified violations. The Client undertakes to enable the Works to be performed by having an appointed person that shall be present at the construction site and shall be responsible for accounting, inspection and acceptance. The Client and the Investor undertake to conduct an inspection of the executed Works within 3 days from notification by the Contractor. If the executed Works are approved by the Client and the Investor, the Investor undertakes to pay for the executed Works according to the terms and conditions in Section 8. 1.5 List of Documents The Parties’ obligations are regulated by the following documents: - This Contract - Appendix 1 Activity Dependent Cost Estimate and Specification Requirements to the present Contract - Appendix 2 The template of the Act of Acceptance to the present Contract The above-mentioned documents complement each other. If conflicting information occurs in the documents, they will be valid in the above order. - Duration of the Contract The Contract will be valid for 10 months from the date of the signing by all Parties or shall be in full force until the obligations of the Parties have been fulfilled. Any extension of the term of the Contract must be notified to the Contractor in writing, at least 2 weeks before the planned expiration of the Contract. The Investor shall not approve requests for time extension for reasons such as but not limited to: - Construction location, conditions and restrictions identified during time of tender and award of the Contract; - Logistics, implementation, coordination problems and other reasons within the control of the Contractor; - Financial, operational and labor difficulties of the Contractor or any of its sub-Contractor/s or supplier/s that are within the Contractor’s or its sub-Contractor’s or supplier/s control. Should such difficulties be due to circumstances beyond the Contractor’s control, such as the quarantine or spread of the COVID-19 disease, the Contractor must inform the Investor of the difficulties and present an action plan on how to solve the difficulties as efficiant as possible; - Any required rectification of non-conforming work items; - Nature and condition of terrain. - Consultation, information and marketing The Parties are committed to consult each other in the extent needed for the successful performance of the assignments stipulated by the Contract. The Contractor shall attend meetings that the Investor and the Client summon when needed. The Parties shall attend meetings with at least the point of contacts stated in Section 1.2 of the Contract, or with a person appointed and authorized by the point of contact or someone with at least the same position as the point of contact, from the Party. The Parties should be ready to attend meetings online, assembled via agreed web conferencing software. The Contractor may not, in any circumstances, use the assignment or the result of any assignments stipulated by the Contract, as reference or in its marketing, without the written approval by the Investor. - Price and delivery terms The Investor shall pay the Contractor for Works according to the prices stated in Appendix 1 to this Contract, all the executed Works that are not written into Appendix 1 to the present Contract could not be paid by the Investor. The Contract Price and unit prices as outlined in Appendix 1 shall be binding and shall not be altered in any event. The Contract Price will be modified only in cases of Investor-approved work variations and shall be reflected in additional agreement to this Contract. The scope of the Works (and the Contract Price in the event its change is caused by a change in the scope of the Works) may be amanded after approval of the technical conditions by the designer. All prices are stated in EUR excluding VAT. The total amount of the Works stipulated by this Contract is ХХХХ,ХХ EUR (ХХХХХХ EUR ХХ cents) VAT excluded. This is a fixed price Contract, no increase of taxes, duties or others will influence the Contract and the price agreed herein, which remain binding. The Contractor shall be liable for its under-estimation of the requirements of this Contract, inflation or currency devaluation, if any. Works are to be delivered no later than 1st of November 2020. The Contractor is obliged to inform the Investor in writing about commencing the execution of Works no later than in 48 hours from the scheduled commencing day. The timeframes of the Works execution shall be set by this Contract. The Time Schedule Chart is an integral part of this Contract, which establishes the commencing and completion dates of all types (stages, complexes) of Works provided by this Contract. The Contractor shall, within 5 calendar days of the signature of this Contract, submit to the Investor and the Client the Time Schedule Chart of Works execution for approval. The Contractor shall provide an updated Time Schedule Chart of the plan of work at the request of the Investor. - Warranties The Contractor further warrants that: - In all circumstances it shall act in the best interests of the Investor; - No third party has received or will receive from, or will be offered by, the Contractor any direct or indirect benefit arising from this Contract; - It has not misrepresented or concealed any material facts in the bidding of this Contract; - All materials used are new, legally sourced and fit for their particular purpose; - No health hazard materials (lead paints etc.) will be used in the course of the construction. Upon the execution of the Works, prior to final acceptance of the Contractor’s delivery on this Contract, and per the tender specifications, the Contractor should furnish the Client the warrantee contract for executed Works and for each additionally installed item of equipment that comprises the warranty certificate from the manufacturer of such item, for the 12-month term starting from the date of signing the Act of acceptance of executed Works by the Parties. Per the procurement specifications should cover all the claims, except for misuse or gross negligence related to normal use or natural wear and tear of the premises or its parts. The warrantee coverage shall cover both shipping, labor, and materials and result in zero out of pocket expense for the Client. Warrantee claims should be processed within 10 working days. For the avoidance of doubt, the warrantee relationship exists purely between the Client and the Contractor. All claims shall be handled directly by the Client. - Acceptance procedure After receipt of a written notification of readiness to transfer the executed Works from the Contractor, the Investor and the Client shall start the procedure of acceptance within three working days, unless another date is agreed upon between the parties. Executed Works shall be accepted in several stages by signing the Act of Acceptance for each such stage. The number of stages and their timeframes shall be agreed by the Investor and the Contractor in the Time Schedule Chart with the signing of the Contract. The Client shall discharge an authorized person to accept the delivery of Works and sign the Act of Acceptance. The Client shall authorize its representative to accept the Works and sign the Act of Acceptance. The Investor shall send his representative to inspect the acceptance of Works. The Act of Acceptance is not valid without the signature of the representative of the Investor. The Investor has the right to completely or partially refuse the acceptance of Works and sign the Nonconformance Act in case of discrepancy of delivered Works or its specifications to the Appendix 1 to present Contract. In case of refusing the acceptance of Works by Investor, the Contractor shall remedy all the discrepancies of Works or its specifications to the Appendix 1 to present Contract within 7 calendar days from the date of receiving the written notification, or another date agreed upon by the Parties. The templates of the Act of acceptance is provided in the Appendix 2 to the present Contract. 7. Payment terms Payment shall only be done according to an invoice. All invoicing shall be done by the Contractor, which means that subcontractors have no right to invoice the Investor. Payment shall be made by bank transfer of the funds in EUR to the Contractor’s bank account and should be made in two stages: 1. Deposit payment in the total amount of ХХХХХ EUR (ХХХХХХ EUR ХХ cents) VAT excluded, that equals to 30% from the total amount of present Contract, shall be paid within 20 (twenty) banking days from the date of signing the Contract by the Parties. 2. Payment in the total amount of ХХХХ EUR (ХХХХХХ EUR ХХ cents) VAT excluded, that equals to 20% from the total amount of present Contract shall be transferred after 50% of Works are executed by present Contract by the Contractor and Contractor has provided following documents for payment processing: - VAT note with a receipt that confirms its registration in ERPN – 1 copy - Acts of Acceptance (Appendix 2) in accordance with the number of Executed Works stages – 3 hardcopies with Parties stamps and signatures - Invoice – 2 hardcopies with Contractor’s stamp and signature - Contractor’s warranty contract for executed Works -1 hardcopy with Contractor’s stamp and signature. - Payment in the total amount of ХХХХ EUR (ХХХХХХ EUR ХХ cents) VAT excluded, that equals to 30% from the total amount of present Contract shall be transferred after 80% of Works are executed by present Contract and Contractor has provided following documents for payment processing: • Acts of Acceptance (Appendix 2) in accordance with the number of Executed Works stages – 3 hardcopies with Parties stamps and signatures. • Invoice – 2 hardcopies with Contractor’s stamp and signature. • Contractor’s warranty contract for executed Works – 1 hardcopy with Contractor’s stamp and signature. 4. Balance payment in the total amount of ХХХХ EUR (ХХХХХХ EUR ХХ cents) VAT excluded, that equals to 15% from the total amount of present Contract shall be paid after the submission of the executive documentation, certificates for materials, as well as the necessary documentation for putting the object into operation, commissioning activities certificates to the Client and providing the necessary documents for payment processing by the Contractor (see clause 2). A payment shall be made only after receipt and approval by the Client all the above-mentioned documents. 5. Final payment in the total amount of XXXX EUR (XXXXX EUR XX cents) VAT excluded, that equals to 5% from the total amount of the present Contract, shall be paid after 30 calendar days from the start of operation of the construction object in the absence of claims by the Investor and providing the necessary documents for payment processing, except for the warranty contract by the Contractor (see clause 2). The Investor is obliged to execute the second and third stage payment to the Contractor within 20 banking days term from the date of receipt of full set of documents needed for providing the payment that should be confirmed by the Investor and/or the Client. The Contractor is responsible for the documentation at the construction site. If fines are imposed by the state bodies based on the results of the inspection, the Contractor compensates the full ammount or this amount is deducted from the total value of the Сontract. In the event the Client representative detects a discrepancy between the construction works and the design documentation or the standards, the Contractor is obliged to compensate the cost of materials and to carry out dismantling and installation works at its own expense, otherwise the loss amount shall be deducted from the total amount of the Contract. The loss amount is estimated by the working commission composed of the representatives of the Investor and the Client. - Taxes and social security contributions The Contractor shall fulfil its obligations regarding payroll taxes and social security contributions in Ukraine and in the country where the Contractor has its registered office. The same applies to all possible subcontractors. - Cancellation In case the Investor intends to cancel Works, in whole or partially, that the Contractor has already started working on/with, the Contractor has the right to be compensated by the Investor for justified costs associated with the work performed. If the Investor cancels the Works, in whole or partially, the Contractor must inform the Investor of risks associated with the cancellation. The Contractor is obliged according to this Contract to finish the Works to such an extent that the Investor sees fit in order to mitigate the risks associated with the cancellation. - Independency The Contractor shall protect and represent the Investor’s and the Client’s interests. The Contractor and/or the Contractor’s personnel may not, during the term of the present Contract, exercise any operations that may undermine the Investor’s and/or the Client’s confidence in any way. The Contractor must immediately inform the Investor and/or the Client if there is reason to believe that circumstances in conflict with this section are or will be occurring. - Ownership and access rights All rights (including amongst others, ownership, access rights and all immaterial rights such as copyright, patent and know-how) to all results and/or materials created by producing the goods or other work which is covered by this Contract, is belonging unrestricted to the Client. The Client thus owns the unrestricted right to dispose of all the work, results, systems, documentation, methods etc. by freely transferring or assigning or otherwise disposing of all such rights and/or results. In addition, summaries and extracts of the results of such work is the Client’s property. Please note that the Investor and the Client grants the Swedish International Development Cooperation Agency, hereinafter referred to as Sida, the right to use free and at no charge and as it sees fit, and in particular, to store, modify, translate, display, reproduce by any technical procedure, publish or communicate by any medium all documents deriving from the Agreement, whatever their form, according to the agreement between Sida and the Swedish Association of Local Authorities and Regions, hereinafter referred to as SKL International. - Responsibility for faults Faults mean all deviations from Appendix 1 to this Contract, other agreed upon requirements regarding the Works, from any of the Contractor issued descriptions or commitments relating to the Works or otherwise from what is professionally intended with the Works. The Contractor undertakes, without any delay and without any compensation, to correct all faults and errors in the executed Works. In the event the Contractor fails to take corrective action within 5 days from notification, upon the request from the Investor, the Investor may remedy the fault at the expense of the Contractor. If the identified faults could not be corrected neither by the Contractor, Investor nor by third Party, the Investor have right to reject the acceptance of such Works and claim damages. - Delays in delivery If the Contractor does not follow agreed schedules, the Contractor shall, with the urgency that the circumstances require, at its own expense, rectify the cause of the delay. If the Contractor does not take these measures to rectify the cause of the delay within 30 working days, the Investor may without prejudice to all its other remedies under the Contract, deduct from the agreed price, as liquidated damages, a sum equivalent to 0,5 per cent from the total amount of undelivered Works specified in the Appendix 1 to this Contract, for each day of delay until actual delivery or performance, up to a maximum deduction of 25 per cent of the total amount of present Contract. Once the maximum is reached, the Investor may terminate the Contract. Furthermore, the Investor is entitled to damages according to Section 14. Liability for damage. The payment of liquidated damages shall not in any way relieve the Contractor from any of its obligations to complete the facilities or from any other obligations and liabilities of the Contractor under the Contract. - Liability for damage The Contractor is responsible for damages caused by fault or negligence of the Contractor, its employees, any subcontractors or others commissioned by the Contractor to deliver the Works according to the Contract. The Contractor shall be liable for damages caused to the Investor or the Client through the fault or negligence of the Contractor, its employees, subcontractors or other persons authorized by the Contractor to deliver the Works, if the Investor provides substantial evidence thereof (photo/video recording), or if the Investor may owe the Client for the reasons above, or if the Investor or the Customer, for the reasons above, may owe to a third party. The Investor or the Customer shall promptly notify the Contractor of such claim. These provisions shall survive termination of this Contract. The Contractor shall ensure that the delivered Works do not infringe the rights of other persons (patents, trademarks, designs, copyright etc.) or applicable laws. Liabilities for damages shall apply per present Contract. No limitation for liability shall apply for infringement of rights, or if there is intent or gross negligence. The above is applicable even if the damage is suffered to a third party. - Force majeure If a party, because of government action, war, strikes, boycotts, blockades or other circumstances that it cannot control that emerged after the signing the Contract, is prevented to fulfil its obligations according to the Contract, it shall, to the extent necessary, be exempt from its obligations. Labour dispute arising out of a party’s breach of a collective agreement may not be invoked as grounds for exemption. The Parties shall immediately inform each other if circumstances that could give rise to the application of this provision occur. As soon as the alleged circumstance has ceased, the Party shall notify the other parties, and immediately resume fulfilment of the delivery of Works. Regardless of what is stated above as reasons for exemption from agreed obligations, a delay of more than three months of an agreed performance, is grounds for premature termination of the Contract, even if the delay is caused by the circumstances described in this section. This section of the Contract is not applicable to the current global spread of COVID-19 or any regulation put in place in order to prevent the spread of COVID-19. This section of the Contract is not applicable to any government action or other measure taken by anyone in relation to the global spread of COVID-19. - Concerted Actions of the Parties Regarding the Spread of COVID-19 Coronavirus Disease in Ukraine Considering the introduction of the quarantine on the Territory of Ukraine by Resolution on Prevention of the Spread of COVID-19 in Ukraine dates 11 March 2020 of the Cabinet of Ministers of Ukraine or other resolutions or measures that might follow, the Parties undertake to develop a plan of concerted actions in the conditions of the spread of COVID-19 coronavirus disease, hereinafter referred to as the Plan. The Plan of concerted actions of the Parties in terms of COVID-19 coronavirus disease shall be developed and agreed by the Parties, taking into account the provisions of the Law of Ukraine “On Amendments to Certain Legislative Acts of Ukraine aimed at Preventing the Outbreak and Spread of Coronavirus Disease COVID-19 as of 17.03.2020 530-IX, Resolution of the Cabinet of Ministers of Ukraine “On Prevention of COVID-19 Coronavirus Spread on the Territory of Ukraine” as of 11.03.2020 No. 211 or any other laws or regulations that are put in place due to the COVID-19 situation and applicable at any time during the Contract period. The Plan of concerted action of the Parties in the context of the spread of COVID-19 coronavirus disease shall be set out by the Parties in the form of a separate document, which is an integral part to this Contract. The Plan of concerted action of the Parties in the conditions of the spread of COVID-19 coronavirus disease shall be developed for a term not less than the quarantine term, determined by the Cabinet of Ministers of Ukraine Resolution No. 211 of 11.03.2020 (with amendments and addenda - if adopted). - Amendments and additions Amendments and additions to the Contract will, for its validity, be approved in writing by the Parties and formalized as an Additional Agreement to this Contract. - Transfer of the Contract The Contractor may not without the written consent from The Investor, partly or fully, transfer or pledge its rights or obligations according to the Contract. The Investor may transfer the Contract to another party which will take over the Investor’s rights and responsibilities due to the Contract fully. Such transfer may be necessary if the EU instructions for the U-LEAD project changes during the term of the Contract. - Premature termination The Investor may by written notification terminate the Contract with immediate effect, or to the day the Investor states, under the following the conditions: - The Contractor’s material breach of its obligations according to the Contract, and the shortcomings are not corrected in an acceptable manner within reasonable time from a written notification; - The Contractor is subject to any of the exclusion criteria stated in section 3.1 in the Request for Tenders; - The Contractor transfers or pledges its rights or obligations according to the Contract without the written consent from the Investor; - The invoices from the Contractor are continuously in breach of the terms and conditions in the Contract, despite objections from the Investor; - The Investor or the Customer/Client has demanded correction in writing, three times or more, within a period of twelve months from the moment of signing the Contract, notwithstanding that the Contractor has hereby taken corrective action in time, or The Contractor has committed a fundamental breach of the Contract, which cannot be rectified. Premature termination of the Contract does not mean that the obligations according to a Contract ends. Grounds for premature termination according to above, gives however the Investor the right to terminate Contact with immediate effect. The Contractor may terminate the Contract, to immediate termination if the Investor has committed a fundamental breach of the Agreement, and the faults have not been remedied in acceptable manner within reasonable time from a written notification to the Investors point of contact according to Section 1.2. If the Investor has terminated the Contract according to paragraphs 1-5 above, the Investor is entitled damages in relation to the Investor’s costs for termination of the Contract, exchange of Contractor and for all additional costs and other damage. - Applicable law The rights and obligations under the Contract are determined by Swedish law. - Dispute Any dispute regarding the interpretation of the present Contract and related legal matters shall be tried by Swedish Arbitration. - Transfer of material The Contractor shall transfer all materials derivng from the Contract to the Client within one week from termination of the Contract. All materials and results of executed Works may freely be used by the Client. - The entry into force The Contract enters into force when authorized representatives for all the Parties have signed three identical written original copies of the Contract. The Contract is concluded in English and translated into Ukrainian. In case of ambiguity English will prevail as original language. The Contract has been written in three identical copies of which each party has obtained one. | Договір на виконання робіт Проект «U-LEAD: САЛАР Підтримка Фази впровадження» 2018-2020 Цей документ підготовлено за фінансової підтримки Європейського Союзу та Швеції - Сторони Компанія SKL International AB, ідентифікаційний код SE556414420101, в особі Йенні Янссон Пірс, керуючого директора, яка надалі іменується «Інвестор» - особа, яка координує проект: організовує, фінансує та контролює виконання робіт, задля досягнення соціального ефекту – проведення ремонтних робіт у приміщенні Центру надання адміністративних послуг у м. Буринь Сумської області. Банківські реквізити: IBAN: SE52 8000 0890 1194 4867 7196 Р/р: 8901-1 944 867 719-6 BIC/Swift: SWEDSESS Банк: Swedbank AB Адреса банку: 105 34 Стокґольм, Швеція і Буринська міська рада Сумської області, в особі міського голови Ладухи Віктора Борисовича, код ЄДРПОУ 04058025, надалі іменується «Замовник» - власник/користувач земельної ділянки, що виконує функцію замовника будівництва, передбачену містобудівним законодавством України, який отримує вихідні дані для проектування об’єкту, затверджує проект будівництва, оформлює документи, що надають право на виконання будівельних робіт, надалі іменуються «Роботи» контролює виконання будівельних робіт, забезпечує здійснення авторського і технічного нагляду під час будівництва об’єкта, приймає в експлуатацію закінчений будівництвом об’єкт, оформлює право власності, відповідає за підключення об’єкту до технічних мереж та укладення договорів на обслуговування об’єкту, а також несе відповідальність під час виконання будівельних робіт на об’єкті, як замовник будівництва в розумінні Закону України «Про регулювання містобудівної діяльності» і «XXXXXX» в особі XXXXXX, яке надалі іменується «Виконавець» - підрядник, який зобов’язаний виконати з використанням власних матеріалів роботи, визначені Розділом 1.3 цього Договору на виконання Робіт, та передати Інвестору та Замовнику закінчені роботи у відповідності до проектно-кошторисної документації, державних будівельних норм та чинного законодавства. Реквізити: «XXXXXX» Адреса: ЄДРПОУ: Адреса банку: SWIFT code: IBAN: уклали цей Договір на виконання Робіт (надалі – «Договір»), зміст якого наведений у розділах нижче. Разом ці три сторони надалі іменуються «Сторони», а кожен окремо – «Сторона». Цей Договір укладено в рамках проекту міжнародної технічної допомоги U-LEAD з Європою: програма для України з розширення прав і можливостей на місцевому рівні, підзвітності та розвитку (Компонент 2 «Створення центрів надання адміністративних послуг та підвищення поінформованості населення про місцеве самоврядування» (продовження фази впровадження), який належним чином зареєстровано у Міністерстві економічного розвитку і торгівлі, номер реєстраційної картки 3722-03. 1.2 Контактні дані Контактна особа від кожної Сторони – це особа, що уповноважена представляти Сторону за всіма питаннями, пов’язаними з виконанням узгоджених у цьому Договорі зобов’язань. SKL International. Вулиця, будинок:; Хорнсгатан 15. Поштовий індекс:; 118 82. Місто:; Стокгольм. Країна:; Швеція. Контактна особа з питань виконання Договору, П.І.Б.:; Олександр Мазуркін. Електронна адреса контактної особи:; alexander.mazurkin@skr.se. Номер телефону контактної особи:; +46 76-1251913. Буринська міська рада. Вулиця, будинок:; Вул. Першотравнева, 1. Поштова адреса:; 41700. Місто:; м. Буринь, Сумська область. Країна:; Україна. Контактна особа з питань виконання Договору, П.І.Б.:; Ладуха Віктор Борисович. Електронна адреса контактної особи:; buryn.rada@ukr.net. Номер телефону контактної особи:; +380668607468. «XXXXXX». Вулиця, будинок:. Поштова адреса:. Місто:. Країна:. Контактна особа з питань виконання Договору, П.І.Б.:. Електронна адреса контактної особи:. Номер телефону контактної особи:. 1.3 Предмет Договору Виконавець зобов'язується забезпечити виконання внутрішніх оздоблювальних робіт (ремонтних робіт), змонтувати систему вентиляції, внутрішні мережі електроживлення, водопостачання та каналізації, виконати роботи по вогнезахисту у приміщенні Центру надання адміністративних послуг за замовленням, робочою документацією і дизайн проектом, попередньо погодженими з Інвестором і Замовником, включаючи постачання матеріалів (надалі іменуються «Роботи»), розрахованих у Додатку 1 «Локальний Кошторис та опис вимог» (надалі іменується «Додаток 1»), за адресою об’єкта ремонтних робіт: м. Буринь, вул. Першотравнева 1, відповідно до умов цього Договору та додатків до нього. Роботи мають надаватися професійно, оперативно та якісно згідно з відповідними очікуваннями Інвестора та Замовника від відомої в цій сфері компанії. Під час виконання зобов’язань за цим Договором Виконавець повинен дотримуватися всіх відповідних законів та підзаконних нормативно-правових актів органів центральної і місцевої влади, які стосуються компанії, що уклала цей Договір, а також положень державних будівельних норм та стандартів, які визначають вимоги до здійснення будівельних робіт. - Обов’язки Виконавець зобов’язується надати Інвестору та Замовнику Роботи відповідно до умов цього Договору та його додатків, які є невід’ємною частиною цього Договору. Обов’язки Виконавця включають наступне: - Виконавець несе відповідальність за охорону об'єкта і збереження матеріалів. Вартість охорони об'єкта повинна бути включена до договірної вартості; - Виконавець несе відповідальність за організацію тимчасового електропостачання та водопостачання для будівельних потреб. Вартість повинна бути включена в загальну суму договору. Витрати, які неможливо передбачити внаслідок дій уряду чи так само через введення Постановою Кабінету Міністрів України «Про запобігання поширенню на території України коронавірусу COVID-19» від 11.03.2020 № 211 карантину на території України чи будь-якими іншими майбутніми постановами, що її замінять, будуть сплачені Інвестором, якщо і тільки якщо Інвестор заздалегідь дав письмову згоду на оплату таких витрат. Тому такі непередбачувані витрати не повинні включатися до загальної вартості Договору; - Виконавець несе відповідальність за організацію тимчасового огородження, проїздів по території будівельного маданчика, та монтаж паспорта об'єкта, який надається Замовником; - Виконавець несе відповідальність за своєчасне і якісне ведення документації на будівельному майданчику; - Виконавець несе повну відповідальність за організацію служби охорони праці на об'єкті, проведення інструктажів, забезпечення робітників засобами індивідуального захисту і т. д. Виконавець повинен протягом 24 годин реагувати на зауваження Замовника або Інвестора та вживати заходів щодо усунення виявлених порушень. Замовник зобов’язується створити умови для виконання Робіт шляхом призначення особи, яка буде присутня під час прийому Робіт та відповідатиме за облік, інспектування та прийомку. Замовник та Інвестор зобов’язуються перевіряти виконані Роботи протягом 3 робочих днів з дня отримання повідомлення від Виконавця про виконання робіт. У разі схвалення виконаних Робіт Замовником і Інвестором, Інвестор зобов’язується оплатити виконані Роботи згідно з умовами Розділу 8. - Перелік документів Обов’язки Сторін регулюються такими документами: - Цим Договором - Додатком 1 «Локальний Кошторис та опис вимог» до цього Договору - Додатком 2 «Зразок акту прийому передачі» до цього Договору Вище названі документи є взаємодоповнюючими. У разі виявлення розбіжностей між документами пріоритетність їх положень слід розглядати у зазначеному вище порядку. - Строк дії Договору Цей Договір діятиме 10 місяців, починаючи з дати його підписання всіма Сторонами, але у будь-якому випадку до повного виконання Сторонами своїх зобовязань за цим Договором. Виконавець має бути проінформований про будь-яке продовження терміну дії Договору у письмовій формі щонайменше за 2 тижні до планованого закінчення строку дії Договору. Інвестор не узгоджує запити на подовження терміну дії Договору з причин, перелічених нижче, при цьому перелік не є вичерпним: - Місцезнаходження об’єкту будівництва, наявність умов та обмежень, що існували та були відомі Сторонам під час проведення тендера та підписання Договору; - Логістика, виконання, координація проблем та інші причини затримки, які є в межах контролю Виконавця; - Фінансові, операційні проблеми та проблеми з персоналом Виконавця або з його субпідрядниками й постачальниками, які знаходяться під контролем Виконавця або його субпідрядників чи постачальників. Якщо такі труднощі пов'язані з обставинами, що не підлягають контролю Виконавця, наприклад, карантин або поширення хвороби COVID-19, Виконавець повинен повідомити Інвестора про труднощі та подати план дій щодо того, як вирішити труднощі як можна ефективніше; - Необхідність виправити роботу неналежної якості; - Природа та умови території. - Консультування, інформація і маркетинг Сторони зобов’язуються консультуватися одна з одною в обсязі, необхідному для успішного виконання завдань, передбачених Договором. Виконавець зобов’язується брати участь у нарадах, які в разі потреби будуть організовувати Інвестор і Замовник. Для участі у нарадах Сторони делегуватимуть, принаймні, тих контактних осіб, що зазначені в Пункті 1.2 цього Договору. Представником Сторони може також бути особа, призначена або уповноважена контактною особою або особою, яка займає, принаймні, таку саму посаду, як і контактна особа. Сторони повинні бути готові брати участь у засіданнях онлайн, що створюються через узгоджене програмне забезпечення для веб-конференцій. За жодних обставин Виконавець не повинен використовувати завдання або результати виконання будь-якого з завдань, передбачених Договором, в якості рекомендації для подальшої роботи або для цілей маркетингу компанії без письмової згоди Інвестора. - Ціна та строки доставки Інвестор здійснює оплату Виконавцю за Роботи за цінами, що наведені в Додатку 1 до цього Договору, Всі виконані Роботи, що не вказані в Додатку 1 до цього Договору не можуть бути оплаченими Інвестором. Вартість Договору за обсяг Робіт та ціна за одиницю, наведені у Додатку 1 є обов’язковими та в жодному разі не можуть бути змінені. Вартість Договору може бути змінена тільки за умови зміни робіт, погодженої Інвестором, про що Сторонами укладається додаткова угода до цього Договору. Обсяг Робіт (та вартість Договору, якщо її зміна спричинена зміною обсягу Робіт) може змінюватися після затвердження технічних умов проектувальником. Всі ціни наводяться в Євро без ПДВ. Загальна вартість Робіт за цим Договором становить ХХХХ,ХХ Євро (ХХХХХХ Євро ХХ центів) без ПДВ. Цей Договір є контрактом з фіксованою ціною - підвищення податків, мит та інших обов’язкових платежів не може впливати на Договір та ціну, погоджену в цьому Договорі, яка залишається обов’язковою для виконання. Виконавець є відповідальним за недооцінку вимог цього Договору, інфляції або валютних коливань, якщо такі мають місце. Роботи повинні бути виконані не пізніше 1 листопада 2020 року. Виконавець зобов’язується проінформувати Замовника про початок виконання Робіт не пізніше ніж за 48 годин до запланованої дати початку виконання Робіт шляхом письмого повідомленя. Строки виконання Робіт встановлюються цим Договором. Невід’ємною частиною цього Договору є календарний графік плану робіт, в якому визначаються дати початку та закінчення всіх видів (етапів, комплексів) Робіт, передбачених цим Договором. Виконавець зобов’язується протягом 5 календарних днів з моменту підписання цього Договору передати на погодження Інвестору та Замовнику календарний графік виконання Робіт. Виконавець надає оновлений календарний графік плану робіт за запитом Інвестора. - Гарантійні зобов’язання Виконавець гарантує: - За будь-яких обставин він діятиме в інтересах Інвестора; - Жодна третя сторона не отримуватиме від Виконавця ніякої прямої або опосередкованої вигоди і не отримає від Виконавця пропозицій щодо такої вигоди, у зв’язку з цим Договором; - Він не приховуватиме та не буде перекручувати будь-які фактичні дані у процесі виконання цього Договору; - Усі використовувані матеріали є новими, отриманими на законних підставах, і відповідають цілі їх використання; - Жодних матеріалів, небезпечних для здоров’я (фарби із свинцем тощо) людей не буде застосовуватися на будівництві. По факту завершення виконання Робіт, але перед оформленням Акту прийому-передачі, відповідно до вимог тендерних процедур, Виконавець повинен надати Замовнику належним чином оформлену гарантію на виконані Роботи та на кожну одиницю встановленого обладнання, яка передбачає гарантію від виробника такого обладнання, строком на 12 місяців або у залежності від сроків, встановлених виробником на ті чи інші обладнання, з дня підписання Акту прийому-передачі виконаних Робіт всіма Сторонами. Відповідно до вимог закупівлі, гарантійнії умови повинні покривати усі гарантійні випадки, окрім випадків не цільового використання та недбалості, які виникатимуть у процесі використання, або природного зносу об’єкту, або його частин. Гарантійні зобов’язання повинні покривати матеріали, вартість заміни та пов’язані транспортні витрати без додаткових виплат Замовника. Гарантійні претензії повинні бути опрацьовані Виконавцем в межах 10 робочих днів з моменту їх отримання. Щоб уникнути сумнів, гарантійні зобов’язання існують тільки між Замовником та Виконавцем. У випадку виявлення недоліків протягом гарантійного строку, Замовник має звертатися безпосередньо до Виконавця з метою усунення таких недоліків. - Процедура приймання Після одержання письмового повідомлення Виконавця про готовність до передачі закінчених Робіт Інвестор та Замовник зобов'язані протягом трьох робочих днів розпочати їх приймання. Закінчені Роботи приймаються у декілька етапів шляхом підписання акту прийому-передачі для кожного окремого такого етапу. Кількість етапів і їх часові рамки узгоджуються Інвестором та Виконавцем на момент підписання цього Договору у календароному графіку виконання робіт, якщо Сторонами не була узгоджена інша дата. Замовник повинен уповноважити свого представника прийняти Роботи та підписати Акт прийому-передачі. Інвестор має відрядити свого представника перевірити прийом Робіт. Акт прийому передачі не набирає чинності без підпису уповноваженого представника Інвестора. Інвестор має право частково, чи повністю відмовитися від прийому Робіт у разі невідповідності Робіт, або їх специфікацій Додатку 1 до цього Договору та скласти Акт Невідповідності. У разі відмови Інвестора від приймання Робіт, Виконавець має усунути всі невідповідності виконаних Робіт, або їх специфікацій Додатку 1 до цього Договору протягом 7 календарних днів з дня отримання відповідності, складеного Інвестором, або іншої дати, узгодженної Сторонами. Зразок акту прийому передачі наданий у Додатку 2 до цього Договору. - Умови оплати Оплата здійснюється тільки відповідно до виставленого рахунку. Всі рахунки виставляються Виконавцем, тобто субпідрядники не мають права виставляти рахунки Інвестору. Оплата здійснюється банківським переказом грошових коштів в Євро на розрахунковий рахунок Виконавця, вказаний в цьому Договорі, трьома етапами: - Передоплата в розмірі XХХХХ Євро (ХХХХХХ Євро ХХ центів) без ПДВ, що становить 30% від загальної суми даного Договору, і повинна бути здійснена протягом 20-ти (двадцяти) банківських днів з моменту підписання цього Договору всіма Сторонами. - Оплата в розмірі ХХХХ Євро (ХХХХХХ Євро ХХ центів) без ПДВ що становить 20% від загальної суми даного Договору, і повинна бути здійснена після виконання Виконавцем 50% обсягу Робіт за даним Договором та після надання Виконавцем всіх необхідніх для оплати документів, а саме: - Податкова накладна з чеком-підтвердженням її реєстрації в ЄРПН – 1 копія - Акти прийому-передачі відповідно до кількості завершених етапів робіт (Додаток 2) – 3 оригінали з печатками та підписами Сторін - Рахунок на оплату – 2 оригінали з печаткою та підписом Виконавця - Гарантійний договір від Виконавця на виконані Роботи – 1 оригінал з печаткою та підписом Виконавця. - Оплата в розмірі ХХХХ Євро (ХХХХХХ Євро ХХ центів) без ПДВ що становить 30% від загальної суми даного Договору, і повинна бути здійснена після виконання Виконавцем 80% обсягу Робіт за даним Договором та після надання Виконавцем: • Акти прийому-передачі відповідно до кількості завершених етапів робіт (Додаток 2) – 3 оригінали з печатками та підписами Сторін. • Рахунок на оплату – 2 оригінали з печаткою та підписом Виконавця. • Гарантійний договір від Виконавця на виконані Роботи – 1 оригінал з печаткою та підписом Виконавця. - Післяоплата в розмірі ХХХХ Євро (ХХХХХХ Євро ХХ центів) без ПДВ що становить 15% від загальної суми даного Договору, і повинна бути здійснена після передачі Замовнику виконавчої документації, сертифікатів на матеріали, гарантійних документів на обладнання, а також необхідної документації для введення об'єкта в експлуатацію, протоколів пусконалагоджуваліних робіт Замовнику та після надання Виконавцем всіх необхідніх для оплати документів (див. п.2). Оплата здійснюється після отримання та підтвердження Замовником усіх вищезазначених документів. 5. Фінальна оплата в розмірі ХХХХ Євро (ХХХХХХ Євро ХХ центів) без ПДВ що становить 5% від загальної суми даного Договору, і повинна бути здійснена після 30 календарних днів з моменту початку експлуатації об’єкта будівництва за умови відсутності претензій з боку Інвестора та після надання Виконавцем всіх необхідніх для оплати документів, за виключенням гарантійного договору від Виконавця (див. п.2). Інвестор здійснює другий та третій платіж на користь Виконавця протягом 20 банківських днів з дати отримання всіх необхідних для оплати документів, підтверджених Інвестором та/або Замовником. Виконавець несе повну відповідальність за ведення документації на будівельному майданчику. У разі накладення штрафів з боку державних органів за результатами проведених перевірок, Виконавець зобов'язується їх компенсувати за власний рахунок або дана сума віднімається з загальної вартості Договору. У разі виявлення службою Замовника невідповідності будівельних робіт проектній документації або державним будівельним нормам та стандартам, Виконавець зобов'язується компенсувати вартість матеріалів і виконати демонтажні і монтажні роботи за свій рахунок або сума збитку вираховується із загальної вартості Договору. Сума збитку визначається робочою комісією у складі представників Інвестора та Замовника. - Податки та відрахування на соціальне забезпечення Виконавець повинен виконувати свої зобов’язання щодо сплати податків та відрахувань на соціальне забезпечення в Україні та країні реєстрації компанії Виконавця. Те саме стосується і всіх можливих субпідрядників. - Анулювання Якщо Інвестор хоче частково або повністю анулювати Роботи, над якими Виконавець вже почав працювати, Виконавець має право на отримання від Інвестора компенсації обґрунтованих витрат, пов’язаних із виконанням роботи. Якщо Інвестор скасовує Роботи повністю або частково, Виконавець повинен повідомити Інвестора про ризики, пов’язані зі скасуванням. Відповідно до цього Договору Виконавець зобов’язаний закінчити Роботи в такій мірі, яку Інвестор вважає за потрібне для зменшення ризиків, пов’язаних із скасуванням. - Незалежність Виконавець має захищати та представляти інтереси Інвестора та Замовника. Виконавець та/або персонал Виконавця не повинні протягом терміну дії цього Договору здійснювати операції, які можуть якимось чином підірвати довіру Інвестора та/чи Замовника. Виконавець повинен негайно сповістити Інвестора та/чи Замовника, якщо є підстави вважати, що виникли або можуть виникнути обставини, які суперечать положенням цього розділу. - Права власності та доступу Всі права (включаючи, зокрема, право власності, права доступу та всі нематеріальні права, такі як авторське право, патентне право та право на ноу-хау) на всі результати та/або матеріали, створені шляхом виробництва товарів або виконання іншої роботи, передбаченої Договором, належать без обмежень Замовнику. Таким чином Замовник має необмежене право розпоряджатися всією роботою, результатами, системами, документацією, методами тощо, вільно передавати, переуступати або іншим чином розпоряджатися всіма подібними правами та/або результатами. Резюме та витримки з результатів такої роботи є також власністю Замовника. Зверніть, будь ласка, увагу на те, що Інвестор і Замовник надають Шведському агентству міжнародного розвитку, яке надалі іменується “Sida”, право на безоплатне та вільне використання вищезазначеного згідно з тим, що воно вважає за потрібне, а саме: зберігати, вносити зміни, перекладати, зображувати, відтворювати за допомогою технічних засобів, публікувати або передавати із застосуванням будь-яких засобів всі документи, утворені в результаті виконання угоди, незалежно від їхньої форми, згідно з домовленостями між Sida та Шведською асоціацією місцевих влад і регіонів, яка надалі іменується SKL International. - Відповідальність за порушення Порушення - це невиконання або неналежене виконання Сторонами умов цього Договору, положень Додатку 1 до цього Договору, інших узгоджених вимог щодо Робіт, будь-якого опису, наданого Виконавцем, зобов’язань щодо виконання Робіт або того, що професійно пов’язано з виконанням Робіт. Виконавець зобов’язується без затримок і без будь-якої компенсації усунути порушення та помилки, що стосуються Робіт, які були допущені з його вини. Якщо у відповідь на запит Інвестора Виконавець не може вжити заходів для виправлення ситуації, яке вимагається Інвестором, протягом 5 днів з дати отримання повідомлення, Інвестор має право усунути порушення силами третіх осіб за рахунок Виконавця. Якщо виявлені недоліки не можуть бути усунені Виконавцем, Інвестором або третьою особою, Інвестор має право відмовитися від прийняття таких робіт та вимагати компенсації збитків. - Затримки з постачанням Якщо Виконавець не дотримується узгоджених графіків виконання Робіт, Виконавець повинен оперативно, згідно з вимогами обставин, усунути причину затримок за свій рахунок. Якщо Виконавець протягом 30 робочих днів не вживає заходів для усунення причини затримок, Інвестор має право без шкоди для всіх інших засобів виправлення ситуації, передбачених Договором, відняти від узгодженої вартості цього Договору в якості оціненої неустойки суму, еквівалентну 0,5 відсотку від загальної ціни невиконаних Робіт, вказаних у Додатку 1 до цього Договору, за кожен день затримки до фактичного постачання або виконання. Розмір такої неустойки не може перевищувати загальної вартості даного Договору. Після досягнення 25 відсотків від загальної вартості даного Договору, Інвестор має право припинити дію Договору. Крім того, Інвестор має право на отримання компенсації за шкоду згідно з розділом 14. Відповідальність за шкоду. Сплата Виконавцем вартості збитків у будь-якому випадку не звільняє його відвиконання своїх зобов’язань з будівництва об’єкту та інших зобовязань за цим Договором. - Відповідальність за шкоду Виконавець несе відповідальність за шкоду, заподіяну з вини або недбалості Виконавця, його співробітників, субпідрядників або інших осіб, яким Виконавець доручив постачати Роботи згідно з цим Договором. Виконавець несе відповідальність за шкоду, заподіяну Інвестору або Замовнику, з вини або недбалості Виконавця, його співробітників, субпідрядників або інших осіб, яким Виконавець доручив постачати Роботи, якщо Інвестор надасть достатні того докази (фото/відео фіксацію), або якщо Інвестор через зазначені вище причини може виявитися винним Замовнику або якщо Інвестор чи Замовник через зазначені вище причини можуть виявитися винними третій стороні. Інвестор або Замовник без зайвих затримок повинен письмово з роз'ясненням та підтвердженням (фото, відео) проінформувати Виконавця про таку вимогу. Ці положення також застосовуються, якщо строк дії Договору закінчився. Виконавець несе відповідальність за те, щоб поставлені Роботи не порушували прав інших осіб (патенти, товарні знаки, дизайнерські рішення, авторські права тощо) або вимоги чинного законодавства України. Відповідальність за збитки повинна застосовуватися згідно з умовами даного Договору. У разі порушення прав через навмисні дії або грубу недбалість винної Сторони, немає жодних обмежень щодо суми виплат у разі встановлення відповідальності за шкоду. Вищезазначене діє навіть, якщо шкоду завдано третій стороні. - Форс-мажор Якщо Сторона через дію обставин непереборної сили, зокрема, але не виключно: дії уряду, війну, страйки, бойкоти, блокади або інші обставини, які знаходяться поза її контролем та виникли після підписання Договору, не може виконати свої зобов’язання за Договором, вона звільняється від своїх зобов’язань у відповідному обсязі на строк дії обставин непереборної сили. Трудовий спір, що виникає внаслідок порушення Стороною положень законодавства про працю та/або умов колективного договору, не може вважатися підставою, яка звільняє Сторону від зобов’язань. Сторони негайно проінформують одна одну про виникнення обставин, які можуть призвести до застосування цього положення. Як тільки обставина, про яку йшлося, припинила свою дію, відповідна Сторона повинна проінформувати про це інші сторони та негайно відновити виконання зобовязань за цим Договором. Незалежно від того, що було зазначено вище в якості причини для звільнення від виконання узгоджених зобов’язань, затримка узгодженого виконання на більше, ніж три місяці, є підставою для дострокового припинення дії Договору, навіть, якщо така затримка викликана дією обставин, зазначених у цьому розділі. Цей розділ Договору не застосовується до поточного глобального розповсюдження COVID-19 або будь-якого іншого регулювання, що застосовується з метою запобігання поширенню COVID-19. Цей розділ Договору не застосовується до будь-яких дій уряду чи інших заходів, що вживаються кимось стосовно глобального поширення COVID-19. - Узгоджені дії Сторін у зв'язку з поширенням на території України коронавірусної хвороби COVID-19 Зважаючи на введення Постановою Кабінету Міністрів України «Про запобігання поширенню на території України коронавірусу COVID-19» від 11.03.2020 № 211 карантину на території України, або інших постанов чи заходів, які можуть бути введенні, Сторони зобов’язуються розробити План узгоджених дій в умовах поширення коронавірусної хвороби COVID-19, надалі іменується «План». План узгоджених дій Сторін в умовах поширення коронавірусної хвороби COVID-19 повинен бути розроблений та узгоджений Сторонами з урахуванням положень Закону України «Про внесення змін до деяких законодавчих актів України, спрямованих на запобігання виникненню і поширенню коронавірусної хвороби COVID-19» від 17.03.2020 № 530-ІХ, Постанови Кабінету Міністрів України «Про запобігання поширенню на території України коронавірусу COVID-19» від 11.03.2020 № 211 або будь-які інші закони чи нормативні акти, які приймаються через ситуацію з COVID-19 та застосовуються в будь-який час протягом періоду дії цього Договору. План узгоджених дій Сторін в умовах поширення коронавірусної хвороби COVID-19 викладається Сторонами у формі окремого документу, який є невід’ємним додатком до цього Договору. План узгоджених дій Сторін в умовах поширення коронавірусної хвороби COVID-19 повинен бути розроблений на строк, що не може бути меншим, ніж строк карантину, визначений Постановою Кабінету Міністрів України від 11.03.2020 № 211 (з подальшими змінами та доповненнями – у разі їх прийняття). - Зміни та доповнення Зміни та доповнення до Договору вважаються дійсними, якщо вони схвалені всіма Сторонами у письмовій формі та оформлені у вигляді Додаткової угоди до цього Договору. - Передача прав та обов’язків за Договором Виконавець не може без письмової згоди Інвестора, частково або повністю, передавати чи відчужувати свої права чи обов’язки за цим Договором. Інвестор може передати права та обов’язки за Договором іншій стороні, яка візьме на себе всі права та обов’язки Інвестора, передбачені Договором. Така передача може бути необхідною, якщо протягом дії Договору зміняться інструкції ЄС щодо проекту «U-LEAD». - Дострокове припинення Інвестор може шляхом письмового повідомлення припинити дію цього Договору, при цьому припинення відбудеться негайно або в день, зазначений Інвестором, за таких обставин: - Виконавець серйозно порушив взяті за цим Договором зобов’язання і не усунув порушення у прийнятній формі протягом розумного періоду часу з моменту отримання письмового повідомлення проусунення порушень від Інвестора та/або Замовника; - Якщо на Виконавця поширюються критерії виключення, зазначені в розділі 3.1 Запиту тендерних пропозицій; - Виконавець передає або відчужує права або обов’язки за Договором без письмової згоди Інвестора; - Рахунки Виконавця постійно виставляються з порушенням умов Договору, незважаючи на заперечення з боку Інвестора; - Протягом дванадцяти місяців з моменту підписання цього Договору Інвестор або Замовник вимагав вжити заходів щодо виправлення ситуації три рази або більше, не дивлячись на те, що Виконавець вживав таких заходів своєчасно або Виконавець істотно порушив Договір, і це порушення не можна усунути. Дострокове припинення строку дії Договору не звільняє Сторін від виконання зобов’язань за цим Договором. Проте підстави для дострокового припинення згідно з вищезазначеним надають Інвестору право на негайне припинення Договору. Виконавець може припинити дію Договору, якщо Інвестор істотно порушив умови цього Договору, і порушення не були усунуті у прийнятній формі протягом розумного періоду часу з моменту надання письмового повідомлення контактній особі Інвестора, визначеній в Пункті 1.2 цього Договору. Якщо Інвестор припинив дію Договору відповідно до зазначених вище пунктів 1-5, Інвестор має право на отримання відшкодування своїх витрат на припинення дії Договору, заміну Виконавця, а також всіх додаткових витрат і втрат. - Право, що регулює угоду Всі права та обов’язки, передбачені цим Договором, регулюються шведським правом. - Вирішення спорів Будь-які спори стосовно інтерпретації Договору та пов’язаних з ним правових питань мають вирішуватися в Шведському арбітражі. - Передача матеріалів Протягом одного тижня з моменту припинення дії Договору Виконавець повинен передати всі матеріали, отримані в результатів виконання Договору, Замовнику. Всі матеріали та результати виконання Робіт можуть вільно використовуватися Замовником. - Набуття чинності Цей Договір набуває чинності з моменту підписання уповноваженими представниками всіх Сторін трьох ідентичних оригінальних примірників угоди. Договір укладений англійською мовою та перекладений українською мовою. У випадку виявлення розбіжностей у перекладі, перевагу матиме англійська мова. Договір складено у трьох ідентичних примірниках, по одному для кожної зі Сторін. |
| --- | --- |
| 23. Підписи Сторін/Signatures of the Parties: |  |
| Від імені Інвестора/For the Investor Йенні Янссон Пірс / Jenny Jansson Pearce ______________ Місце і дата/Place and date | Від імені Замовника/For the Client Ladukha Viktor Borysovych / Ладуха Віктор Борисович ______________ Місце і дата/Place and date |
| Від імені Виконавця/For the Contractor XXXXXX / XXXXXX ____________________ Місце і дата/Place and date |  |